## Bruce
| Monday: 9/3/2018 | Tuesday:9/4/2018 | Wednesday:9/5/2018 | Thursday:9/6/2018 | Friday:9/7/2018 |  | Monday:9/10/2018 | Tuesday:9/11/2018 | Wednesday:9/12/2018 | Thursday:9/13/2018 | Friday:9/14/2018
AM | Labor day | Travel back to DC area. | 1. Generate Stack File from latest FDIIS and PROBE data. 2. Work with Ms. Collins to get an invoice processed for Tableau Desktop license | 1. Work with ABO regarding data sharing 2. Begin to integrate ABO data into G8 reporting 3. Assist with any requested changes in latest Stack File | 1. Continue with Stack Tool development | AM | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project
PM | 2. Labor day | Travel back to DC area. | 3. Review latest Stack File with Tom Henion | 4. Work with Rich and Jake in order to evaluate progress on the Transparency Project for FDP Team | 2. Continue to work on the integration of ABO and G8 data | PM | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project | 1. Continue to integrate ABO and G8 data into reporting; 2. Continue with Stack Tool development; 3. Continue working on Transparency Project for FDP Team 4. Continue to assist with SharePoint development and Quad Charts as needed; 5. Work with Tableau Desktop to ensure we are ready to go with Transparency Project
PM |  |  | 4. Demo Stack Tool​ and assist with SharePoint and Quad Charts where needed | 5. Continue with Stack Tool development and working in Tableau | 4. Continue with Stack Tool development and working in Tableau | PM
Timeline…. Stack Tool Demo to be completed by 9/5/2018 or 9/06/2018.
| Task | Start | End | Status
DEV
| Stack Tool Demo | 2018-09-05 | 2018-09-05 | Not Started
| Transparency Project | 2018-09-04 | 2018-10-01 | In Progress
| ABO Data Sharing | 2018-08-31 | On going | In Progress
QA
| Generate Stack File | 2018-09-05 | 2018-09-06 | Not Started
PROD
| Stack File | 2018-09-05 | 2018-09-06 | Not Started

## Shaun
| Monday: 9/3/2018 | Tuesday:9/4/2018 | Wednesday:9/5/2018 | Thursday:9/6/2018 | Friday:9/7/2018 |  | Monday:9/10/2018 | Tuesday:9/11/2018 | Wednesday:9/12/2018 | Thursday:9/13/2018 | Friday:9/14/2018
AM | Holiday | 1. Created Quad Schedule | 1. Build out Quad prototype at Teksouth site | 1. Build out Quad prototype at Teksouth site | 1. Build out Quad prototype at Teksouth site | AM | 1. Access MilTech's SharePoint environment | 1. Build G-8 site portal | 1.Create G-8 SharePoint permissions groups(SSO, Budget,etc) | 1. Import data BOS Root, FDIIS LQA & FDIIS QTY data sources | 1. Import data BOS Root, FDIIS LQA & FDIIS QTY data sources
PM | Holiday | 2. Requirements meeting with Tom to prioritize requirements for basis of Quad schedule | 2. Meeting with Tom defining G-8 SharePoint permissions groups and site structure. | 1. Build out Quad prototype at Teksouth site | 1. Build out Quad prototype at Teksouth site | PM | 2. Build G-8 site portal | 2. Build G-8 site portal | 2. Create G-8 SharePoint permissions groups(SSO, Budget,etc) | 2. Import data BOS Root, FDIIS LQA & FDIIS QTY data sources | 2. Import data BOS Root, FDIIS LQA & FDIIS QTY data sources
|  | 3. Pending digital signatures from ESD regarding SharePoint environment | 1. Build out Quad prototype at Teksouth site | 1. Build out Quad prototype at Teksouth site | 1. Build out Quad prototype at Teksouth site
G-8 SharePoint Quad Schedule
No. | Task | Start | End | Status | Dependencies
SharePoint Development Environment
SharePoint Development Environment
1 | Access to MilTech SharePoint Environment | 2018-09-04 | 2018-09-07 | Current
2 | Define G-8 SharePoint site structure | 2018-09-04 | 2018-09-07 | Current | 1
3 | Build G-8 site portal | 2018-09-10 | 2018-09-14 | Not Started | 1
Permissions
4 | Define G-8 SharePoint permissions groups (SSO, Budget,etc) | 2018-09-04 | 2018-09-07 | Not Started | 3
5 | Create G-8 SharePoint permissions groups(SSO, Budget,etc) | 2018-09-10 | 2018-09-14 | Not Started | 3
Data Connections
6 | Import data BOS Root, FDIIS LQA & FDIIS QTY data sources | 2018-09-10 | 2018-09-14 | Not Started | 3
Business Logic
7 | Develop feature to capture yearly, monthly, weekly, daily cycles | 2018-09-03 | 2018-10-01 | Not Started | 3
8 | Develop feature to split out RDTE, PROC, OTHER and TOTAL values | 2018-09-03 | 2018-10-01 | Not Started | 3
9 | Develop feature to restrict creating Programs within one or more portfolios | 2018-09-03 | 2018-10-01 | Not Started | 3
10 | Develop feature to assign and omit Key 4 records within a Program | 2018-09-03 | 2018-10-01 | Not Started | 3
11 | Develop feature for system to calculate total dollar value per fiscal year for Key 4(s) selected for Program | 2018-09-03 | 2018-10-01 | Not Started | 3
12 | Develop feature for LINs to be selectable to a Program | 2018-09-03 | 2018-10-01 | Not Started | 3
13 | Create SharePoint Program list | 2018-09-03 | 2018-10-01 | Not Started | 3
14 | Develop feature to create, update and remove a Program | 2018-09-03 | 2018-10-01 | Not Started | 3
15 | Develop feature to allocate, deallocate Key 4 to and from Program | 2018-09-03 | 2018-10-01 | Not Started | 3
16 | Develop feature for Key 4 values allocated to appropriate FY fields | 2018-09-03 | 2018-10-01 | Not Started | 3
17 | Develop feature for system to sum LIN quantities | 2018-09-03 | 2018-10-01 | Not Started | 3
User Interface/Experience
18 | Develop feature to allow SSO to create a Program | 2018-09-03 | 2018-10-01 | Not Started | 3
19 | Develop feature to display a list of Programs | 2018-09-03 | 2018-10-01 | Not Started | 3
20 | Develop feature for Key 4 to be available or not for other Programs | 2018-09-03 | 2018-10-01 | Not Started | 3
21 | Develop feature for a Program to require a name | 2018-09-03 | 2018-10-01 | Not Started | 3
22 | Develop feature to allow SSO that Program have been identified properly and ready for manual input by other offices | 2018-09-03 | 2018-10-01 | Not Started | 3
23 | Develop feature that program is ready for manual input by other offices | 2018-09-03 | 2018-10-01 | Not Started | 3
24 | Develop feature to allow SSO to set amount fields to reflect remaining balance of each Key 4 that has not split to another Program | 2018-09-03 | 2018-10-01 | Not Started | 3
25 | Develop feature to allow SSO to split Key 4 record and only assign some of the dollar values to a Program | 2018-09-03 | 2018-10-01 | Not Started | 3
26 | Develop feature to display Key 4 records that fall within a selected root | 2018-09-03 | 2018-10-01 | Not Started | 3
27 | Develop archive feature to access historical Programs | 2018-09-03 | 2018-10-01 | Not Started | 3
28 | Develop G-8 web site design | 2018-11-02 | 2018-11-09 | Not Started | 3
Presentation
29 | Build SharePoint presentation library | 2018-10-01 | 2018-11-01 | Not Started | 3
30 | Develop User Interface for Presentation Export View | 2018-10-01 | 2018-11-01 | Not Started | 3
31 | Develop feature to export data from SharePoint to PowerPoint slide | 2018-10-01 | 2018-11-01 | Not Started | 3
32 | Develop feature to generate PowerPoint slides containing Key 4 and LIN data associated with a Program | 2018-10-01 | 2018-11-01 | Not Started | 3
SharePoint QA Environment
SharePoint Development Environment
33 | Import G-8 site portal from development environment to QA environment | 2018-11-12 | 2018-11-16 | Not Started | 3
Permissions
34 | Import SharePoint Groups (SSO, Budget,etc) | 2018-11-12 | 2018-11-16 | Not Started | 3
35 | Test user permissions(Windows Authentication/AKO) | 2018-11-12 | 2018-12-01 | Not Started | 3
Data Connections
36 | Import data BOS Root, FDIIS LQA & FDIIS QTY data sources to QA environment | 2018-11-12 | 2018-11-16 | Not Started | 3
37 | Test data connections | 2018-11-12 | 2018-12-01 | Not Started | 3
Business Logic
38 | Import Quad Chart business logic features to QA | 2018-11-12 | 2018-11-16 | Not Started | 3
39 | Test Quad Chart business logic features in QA | 2018-11-12 | 2018-12-01 | Not Started | 3
Presentation
40 | Import presentation features to QA environment | 2018-11-12 | 2018-11-16 | Not Started | 3
41 | Test presentation features in QA environment | 2018-11-12 | 2018-12-01 | Not Started | 3
User Interface/Experience
42 | Import user interface features to QA environment | 2018-11-12 | 2018-11-16 | Not Started | 3
43 | Test user interface features in QA environment | 2018-11-12 | 2018-12-01 | Not Started | 3
User Training
44 | Create user training SharePoint site | 2018-09-10 | 2018-09-14 | Not Started | 3
45 | Email SharePoint training links to G-8 personnel | 2018-09-10 | 2018-09-14 | Not Started | 3
User Manual
46 | Create User Manual for Quad Solution | 2018-11-19 | 2018-11-23 | Not Started | 3
SharePoint Production Environment
SharePoint Development Environment
47 | Import G-8 site portal from development environment to QA environment | 2018-12-03 | 2018-12-07 | Not Started | 3
Permissions
48 | Import G-8 SharePoint permissions groups | 2018-12-03 | 2018-12-07 | Not Started | 3
49 | Validate user permissions(Windows Authentication/AKO) | 2018-12-03 | 2018-12-21 | Not Started | 3
Data Connections
50 | Import data BOS Root, FDIIS LQA & FDIIS QTY data sources to Production environment | 2018-12-03 | 2018-12-07 | Not Started | 3
Business Logic
51 | Import Quad Chart business logic features to production | 2018-12-03 | 2018-12-07 | Not Started | 3
Presentation
52 | Import Quad Chart business logic features to production | 2018-12-03 | 2018-12-07 | Not Started | 3
User Interface/Experience
53 | Import User Interface features to production | 2018-12-03 | 2018-12-07 | Not Started | 3

## Amanda
| Monday: 9/3/2018 | Tuesday:9/4/2018 | Wednesday:9/5/2018 | Thursday:9/6/2018 | Friday:9/7/2018 |  | Monday:9/8/2018 | Tuesday:9/9/2018 | Wednesday:9/10/2018 | Thursday:9/11/2018 | Friday:9/12/2018
AM | Labor day | 1. Gathering data for the Develop manuals, guides, and smart cards in support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides | 1. continued to prepared documentation and setup electronic folders on Army G8 system that will ensure continuity on program and project documentation | 1. Gathering data for the Develop manuals, guides, and smart cards in support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides | 1. continued to prepared documentation and setup electronic folders on Army G8 system that will ensure continuity on program and project documentation | AM | 1.Gathering data for the Develop manuals, guides, and smart cards in support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides | Gathering data for the Develop manuals, guides, and smart cards in support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides | Gathering data for the Develop manuals, guides, and smart cards in support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides | Gathering data for the Develop manuals, guides, and smart cards in support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides | 1. continued to prepared documentation and setup electronic folders on Army G8 system that will ensure continuity on program and project documentation
PM | 2. Labor day | 2. calendar completed | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | PM | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site. | 2. Provide support to Bruce and Shawn; Build out of SharePoint Quad Chart prototype solution in Teksouth SharePoint site.
|  | 3. Communication with PM on Shaun status | 3. Communication with PM on Shaun status provisioning of new environment.​ | 3. Communication with PM on Shaun status | 3. Communication with PM on Shaun status |  | 3. Communication with PM on Teksouth Visitors status | 3. Communication with PM on Teksouth Visitors status | 3. Communication with PM on Teksouth Visitors status . | 3. 3. Communication with PM on Teksouth Visitors status | 3. Communication with PM on Teksouth Visitors status
Timeline…. 3 wks to complete Gathering data for the Develop manuals, guides, and support of the tool to include: a) User Manual, b) Operations Manual/Guide, c) Training Manual (step-by-step guide), d) Task Guides
| Task | Start | End | Status
DEV
| Gathering data for the Develop manuals | 2018-09-04 | 2018-09-21 | In Progress
| Develop manual guides and support | 2018-09-04 | 2018-09-21 | In Progress
| User maunul | 2018-09-04 | 2018-09-21 | In Progress
|  |  | 2018-09-21 | In Progress
| Step by Stop | 2018-09-04 | 2018-09-21 | In Progress
| Operation Manual/Guide |  |  | Not Started
QA
N/A
PROD
N/A

## Sheet1
Task | Start | End | Status | DEV | QA | PROD
DEV |  |  |  | SharePoint Development Environment | SharePoint Quality Assurance Environment | SharePoint Production Environment
Develop SharePoint G-8 Quad Project
Import G-8 data from Access Database to TekSouth SharePoint Site | 2018-08-20 | 2018-08-20 | Complete
Complete version 1 of prototype at TekSouth SharePoint Site | 2018-08-21 | 2018-08-31 | In Progress
Provisioning of MilTech Sharepoint Farm
Communicate with farm admins to stand up SharePoint farm | 2018-08-20 | 2018-08-31 | In Progress
Present G-8 Quad Project SharePoint Solution
Demo to Tom(Date will depend on Tom's availability) | 2018-08-27 | 2018-08-31 | Not Started
QA
N/A
PROD
N/A